## Slide 1: Situation assessment in planning Health promotion project
ทพญ.สุรัตน์ มงคลชัยอรัญญา
สำนักทันตสาธารณสุข กรมอนามัย
30 มกราคม 2562
รร เอเชีย (ราชเทวี)

## Slide 2: การวางแผนโครงการส่งเสริมสุขภาพ (planning a health promotion project)
STEP 1: MANAGE THE PLANNING PROCESS
  เพื่อจัดทำแผน/โครงการ ujczoto develop a plan to manage stakeholder participation, timelines, resources, and determine methods for data-gathering, interpretation, and decision making
STEP 2: CONDUCT A SITUATIONAL ASSESSMENT
  to learn about the population of interest, trends, and issues that may affect implementation, including the wants, needs, and assets of the community.
STEP 3: IDENTIFY GOALS, POPULATIONS OF INTEREST, OUTCOMES AND OUTCOME OBJECTIVES
  to determine goals, populations of interest, outcomes and outcome objectives.

## Slide 3: planning a health promotion program
STEP 4: IDENTIFY STRATEGIES, ACTIVITIES, OUTPUTS, PROCESS OBJECTIVES AND RESOURCES
  to select strategies and activities, feasible with available resources, that will contribute to your goals and outcome objectives.
STEP 5: DEVELOP INDICATORS
  to develop a list of variables that can be tracked to assess the outcome and process objectives have been met.
STEP 6: REVIEW THE PROGRAM PLAN
  to clarify the contribution of each component of the plan to its objectives, identify gaps, ensure adequate resources, and ensure consistency with the situational assessment findings.
Six_steps_planning_health_promotion_programs_2015.pdf

## Slide 4: Competency of public health practitioner
public health practitioners should be able “…to collect, assess, analyze and apply information…to make evidence-based decisions…and make recommendations for policy and program development.

## Slide 5
A situational assessment is a systematic process to gather, analyze, synthesize and communicate data to inform planning decisions
Information from a situational assessment can be used to inform the goals, objectives, target audiences and activities of a health promotion strategy.
Focus On: Six strategic steps for situational assessment

## Slide 6: Why conduct the Situational assessments?
Situational assessments are carried out to:
• Learn more about a population of interest (i.e., who's most affected by a certain health issue)
• Anticipate trends and issues that may affect the implementation of a strategy
• Identify community wants, needs, and assets
• Set priorities
• Inform pending decisions regarding a strategy
• Help write funding proposals

## Slide 7: Step 1: Identify key questions
To determine what you need to inform planning decisions
What is the situation?
current situation and its impact
groups of people are at higher risk of health problems
settings or situations are high risk
steakeholders’ interests, mandates, current activities
Needs, perceptions and supported directions of key influential members, and the community-at-large

## Slide 8
2. What influences are making the situation better and worse?
What high-risk or negative health behaviours
underlying causes or conditions are driving these behaviours
( both +ve and -ve)
strengths and weaknesses of your organization affect the actions
opportunities and threats of the environment affect the actions

## Slide 9
What possible actions can you take to address the situation
other organizations doing / done in the past
มีใครทำอะไรอยู่ในเรื่องที่เกี่ยวข้อง มีการประเมินผลที่เกิดขึ้นไหม

## Slide 10: Step 2: Develop a data gathering plan
to organize sources of data, tasks, and persons responsible
diverse types of data
different methods of data collection
varied sources of data

## Slide 11: Step 3: Gather the data
two types of data collection - primary and secondary data collection
Primary data is data that you and your situational assessment team collect yourselves; for example, via surveys, key informant interviews or focus groups
Train, skill , to get correct and consistency data
data collection is standardized and done ethically, including documenting informed consent.
Secondary data: A literature search, ระบบรายงาน, รายงานประจำปี

## Slide 12: Step 4: Organize, synthesize and summarize the data
to organize information is to arrange the data according to your original key questions
A SWOT (Strengths, Weaknesses, Opportunities, Threats) analysis or a Force Field Analysis can help to determine facilitators and barriers to improving the situation
If possible, summarize findings in a paragraph or five to six bullet points. This will offer others a quick understanding of results and can be useful in any communication products that you develop.

## Slide 13: Step 5: Communicate the information
communicate key findings to each of your stakeholders in a manner that is understandable to each distinct audience.
One strategy is to develop a communication plan which includes your key audience, communication objectives, channels, and communication products

## Slide 14: Step 6: Consider how to proceed with planning
perceive your ability to affect the situation with the available time, financial resources and mandate
gaps in data quality or quantity, relative to stakeholder expectations
next steps in the planning process